After-Action Report — Switch 0 Core Replacement

Project: Cisco 4510 → Dual Aruba 6300 (VSF)
Prepared by: Dr. Mark Bojeun, CIO (SCCC)
Audience: SCCC leadership and OculusIT project team
Date: August 2025

Executive Summary

SCCC replaced the end-of-life Cisco 4510 “Switch 0” with two Aruba 6300 switches in a VSF pair. The first planned cutover (a 24-hour maintenance window on July 3–4, 2025) was aborted at ~11:59 PM July 3 (“no-go”) after the off-site lead was unavailable. A second attempt was executed later using a compressed, “all-at-once” approach rather than the pre-authored six-phase plan. While Wi-Fi and phones were restored by early morning, several VLANs, routing defaults, and building networks were impaired into Monday, requiring substantial manual remediation across campus.

This report documents the events, the plan vs. execution, the technical and process issues observed, and concrete improvements.

Scope & Objectives

- Replace Cisco 4510 with dual Aruba 6300 (VSF) to remove a single point of failure, simplify routing, and modernize security. (See VSF phased strategy + files.)

Precipitating Incident (context)

- May 25, 2025—catastrophic failure: a power loss caused the Cisco 4510 to power down and lose configuration. Repairs ran ~12 hours (1 AM–1 PM); enterprise services including phones and online tools for remote students were impacted for the first ~6 hours. Diagnosis/repair were performed by Dr. Mark Bojeun and remote engineer Frank Kumar; Frank is the same SME later reassigned to other engagements by his management. (Provided from CIO’s log; not captured with timestamps in the meeting transcript.)

Planning & Preparation

- 60-day planning period culminating in a 24-hour maintenance window (July 3–4) for a full conversion; off-site lead (Frank) was unavailable and non-responsive leading into the window.SCCC-Switch-Zero-After-…

- A six-phase implementation plan and per-phase configuration files were prepared to reduce risk and allow rollbacks; this phased plan was not used during the later cutover.SCCC-Switch-Zero-After-…

- A formal post-migration test plan existed but was not executed during the cutover (see attached checklist).SCCC-Switch-Zero-After-…SCCC-Switch-Zero-After-…

Event Timeline (fact-based)

- July 3, ~midnight: Within the 24-hour window, concern about the configuration leads to a no-go (aborted) decision; off-site SME (Frank) is unavailable/non-responsive over the holiday period.

- Weekend following the no-go: New Aruba configs were rebuilt from scratch and a phased approach with rollbacks was requested, including six discrete phases.SCCC-Switch-Zero-After-…

- Second attempt (later Friday night): Access delays ~2 hours; at ~1 AM the team is directed to move all cables (abandoning phased plan). At ~2 AM a rollback was suggested; decision made to continue due to time/complexity.SCCC-Switch-Zero-After-…SCCC-Switch-Zero-After-…

- ~4:30 AM: Wi-Fi across buildings and phones were observed up; SIP path concerns surfaced; on-site testing continued absent a formal test plan.SCCC-Switch-Zero-After-…

- Monday morning: Admin offices (e.g., Admissions/Registration/Finance) down on LAN until default-gateway changes were applied across many access switches (2.5 → 2.1). SCCC manually updated numerous devices (SSH where possible; console otherwise).

- ALC/other buildings: Additional redistribution/routes for several VLANs (e.g., 772/773/775) were missing and later corrected (EIGRP→OSPF/Nexus prefix-list).SCCC-Switch-Zero-After-…

- Follow-through: SME continuity gaps (no proactive follow-up calls; new engineer added Monday) prolonged stabilization.

Note on resourcing: This was the second attempt; the original SME (Frank Kumar)—who co-recovered the 5/25 incident—was reassigned to other projects by his management and unavailable during the critical July 3–4 window. New personnel were introduced who were unfamiliar with SCCC’s campus layout and 25-year history of the core switch. (SME reassignment detail provided by CIO; unrecorded in the meeting transcript.)

Technical Observations

- Routing model mismatch (OSPF scale): Aruba OSPF supports 63 interfaces; legacy Cisco used ~100—a known risk raised pre-cutover.

- Default gateway divergence: Many access switches relied on VLAN1 dual IPs (…2.5 and …2.1). New core design constrained to a single interface/gateway, causing widespread LAN outages until bulk updates were made.

- Missing/undistributed routes: Certain VLANs (e.g., 772/773/775) lacked routing into OSPF and required redistribution/prefix-lists on Nexus to restore DHCP/IP reachability.SCCC-Switch-Zero-After-…

- Configuration delivery: The rolled configuration used at cutover was not provided for on-site peer review beforehand; later access revealed drift from the intended phased approach.

- Test discipline: A formal test plan existed but was not run; ad-hoc testing created false confidence at 4–5 AM and missed building-LAN issues that surfaced Monday.SCCC-Switch-Zero-After-…

- Phased plan bypassed: Despite a documented six-phase, rollback-friendly path, execution shifted to a single big-bang port/cable move around 1 AM—removing rollback safety nets.SCCC-Switch-Zero-After-…SCCC-Switch-Zero-After-…

Impact

- Operations: Monday morning, admin offices could not work until gateway corrections were made; additional buildings (e.g., ALC) required routing fixes.

- Scale of rework: Dozens of switches (estimated 30–50) needed hands-on changes, some by console due to loss of remote manageability.

- What stayed up: By ~4:30 AM, phones and Wi-Fi were up across buildings, limiting public-facing disruption while wired LAN issues persisted.

What Went Well

- Rapid on-site response and persistence through the night, including field testing in multiple buildings.SCCC-Switch-Zero-After-…

- Post-event troubleshooting (e.g., VLAN route redistribution) restored critical off-campus sites (ALC).SCCC-Switch-Zero-After-…

- VSF architecture (once stable) provides the intended redundancy/security benefits vs the single-chassis Cisco 4510 (see design summary).

Issues & Root Causes (technical and process)

- SME continuity gap: Primary SME (Frank) was unavailable/reassigned during the first window; subsequent staff lacked site history. (Per CIO record; supported generally by transcript noting Frank’s absence.)

- Plan/execution mismatch: Six-phase plan + rollback points existed but were not executed; cutover became big-bang at 1 AM.SCCC-Switch-Zero-After-…SCCC-Switch-Zero-After-…

- Pre-cutover review: Config not shared for CIO/onsite review ahead of deployment, reducing catch of gateway and routing pitfalls.

- Test governance: Checklist not run; acceptance gates not met before declaring success; Monday “surprises” followed.SCCC-Switch-Zero-After-…

- Design deltas not fully mitigated: OSPF scale (63) vs legacy (100), multi-IP default-gateway habit in VLAN1, and VLAN redistribution gaps weren’t neutralized before cutover.SCCC-Switch-Zero-After-…

Process Improvements (actionable)

- Enforce phased cutovers with per-phase rollbacks (re-adopt the six-phase VSF plan; no “all at once” unless explicitly risk-accepted by CIO).

- Pre-cutover peer review + freeze: Require T-48h delivery of configs for joint review/sign-off (CIO + onsite + remote lead).

- Run the test plan before “done”: Execute Network Testing Checklist (911, fire/HVAC, VOIP, VLANs, inter-building routing, DHCP/DNS, server VLANs, wireless, etc.) and record pass/fail before declaring success.SCCC-Switch-Zero-After-…

- SME coverage plan: Confirm primary + backup engineers are scheduled and reachable; avoid holiday windows unless explicitly staffed.

- Acceptance criteria & comms: Define clear go/no-go gates, a call-tree, hourly status checks, and mandatory next-business-day follow-up.

- Design hardening prior to cutover:

  - Map OSPF interface counts and summarize where needed.

  - Normalize default-gateway strategy (single authoritative gateway per VLAN) and pre-stage changes to access switches.

  - Validate route redistribution (EIGRP/OSPF/Nexus) with dry-runs.

- Artifacts: Keep a runbook with rollback steps per phase; archive configs and test evidence.

Open Items / Next Steps

- Document final, working configs and publish to SCCC + OculusIT.

- Campus-wide verification run of the Network Testing Checklist, capturing evidence.SCCC-Switch-Zero-After-…

- Post-mortem workshop (SCCC + OculusIT) to bake improvements into standard playbooks.

- Schedule adherence: future core changes will default to phased plans unless CIO signs a risk exception.

Appendices (attached)

- Network_Testing_Checklist.md — comprehensive post-migration verification suite.SCCC-Switch-Zero-After-…

- VSF_Phase_Configuration_Summary.md — six-phase plan, timelines, verification/rollback.

Notes on Evidence

- Statements about the planned 60-day prep, July 3–4 24-hour window, SME unavailability, the phased plan being ignored, rollback discussion at ~2 AM, phones/Wi-Fi observed up ~4:30 AM, and Monday LAN fixes are drawn from the after-action meeting transcript:
SCCC-Switch-Zero-After-…SCCC-Switch-Zero-After-…

- The 11:59 PM “no-go” timestamp and SME reassignment by management, plus May 25 incident specifics, are added from CIO operational records (not timestamped in the transcript).

### Technical Fault Log

| # | Issue Description | Root Cause | Affected VLAN(s) / Services | Resolution Applied | Prevention Measure |
| --- | --- | --- | --- | --- | --- |
| 1 | Administrative offices without wired connectivity on Monday | Routing table inconsistencies – access switches pointed to different default gateways; new core only had one | Multiple admin building VLANs | Manual reconfiguration of default route on ~30–50 switches via SSH/console | Map and migrate all static/default routes during cutover; run “Routing & Connectivity” tests from checklist |
| 2 | Adult Learning Center offline | Missing VLAN routes (772, 773, 775) in deployed configuration | VLAN 772, VLAN 773, VLAN 775 | Added missing VLAN routes on Nexus and redistributed into OSPF | Compare pre/post VLAN list; run VLAN audit before cutover |
| 3 | Cosmetology building Ethernet offline | Routing mismatch and/or missing VLAN config | VLANs for Cosmetology wired network | Updated routing; replaced Aruba switch; verified VLAN presence | Include building-specific wired connectivity tests |
| 4 | Sporadic building outages | Default route inconsistencies across switches; missing VLAN routes | Multiple building VLANs | Per-switch route corrections; VLAN updates on core | Automated discovery of gateway configs prior to migration |
| 5 | Security VLANs unverified during cutover | No execution of full security VLAN tests | VLAN 348–353 (cameras), VLAN 372–377 (access control) | Verified and corrected in follow-up | Immediate post-cutover verification of all safety/security VLANs |
| 6 | No formal test execution | Change of plan to all-in-one migration; no assigned test lead | All VLANs/services | Ad hoc testing only | Assign testing lead; execute and sign off on each section of checklist |
| 7 | No rollback capability mid-cutover | Moved all cables at once | All services | Rollback impractical | Maintain per-phase rollback scripts; avoid big-bang migration for core infrastructure |

APPENDIX – A

NETWORK TESTING CHECKLIST – NOT PROVIDED OR PERFORMED

# NETWORK TESTING CHECKLIST

## Post-Migration Comprehensive System Verification

**Date:** _______________

**Tested by:** _______________

**Start Time:** _______________

**End Time:** _______________

---

## TESTING PRIORITY LEVELS

**CRITICAL:** Must work - business essential, safety critical

**HIGH:** Important for operations - significant business impact

**MEDIUM:** Standard operations - moderate business impact

**LOW:** Non-essential - minimal business impact

---

## SECTION 1: EMERGENCY SYSTEMS (CRITICAL - TEST IMMEDIATELY)

### 1.1 Emergency Calling Systems

- [ ] Test 911 calling from A Building

- [ ] Test 911 calling from AA Building

- [ ] Test 911 calling from S Building

- [ ] Test 911 calling from H Building

- [ ] Test 911 calling from COS Building

- [ ] Test 911 calling from V Building

- [ ] Test 911 calling from SLC Buildings

- [ ] Test 911 calling from B Building

- [ ] Test 911 calling from M Building

- [ ] Test 911 calling from C Building

- [ ] Test 911 calling from E Building

- [ ] Test 911 calling from T-Building Complex

- [ ] Test 911 calling from CAH Building

**Notes:** ________________________________________________

### 1.2 Fire Safety Systems (VLAN 818)

- [ ] Test fire alarm panel connectivity

- [ ] Verify fire alarm monitoring systems

- [ ] Test emergency notification systems

- [ ] Verify fire department notification

- [ ] Test emergency lighting systems

**Notes:** ________________________________________________

### 1.3 HVAC Control Systems (VLAN 817)

- [ ] Test HVAC control for A Building

- [ ] Test HVAC control for AA Building

- [ ] Test HVAC control for S Building

- [ ] Test HVAC control for H Building

- [ ] Test HVAC control for academic buildings

- [ ] Test HVAC control for administrative buildings

- [ ] Verify building automation server connectivity

**Notes:** ________________________________________________

---

## SECTION 2: CRITICAL INFRASTRUCTURE (CRITICAL - TEST NEXT)

### 2.1 Server Network Connectivity

- [ ] Ping test to main servers (10.40.1.1) - VLAN 401

- [ ] Ping test to printers (10.40.2.1) - VLAN 402

- [ ] Ping test to Citrix servers (10.40.3.1) - VLAN 403

- [ ] Ping test to VMotion network (10.40.4.1) - VLAN 404

**Notes:** ________________________________________________

### 2.2 Authentication and Directory Services

- [ ] Test domain controller connectivity

- [ ] Verify user authentication and login

- [ ] Test group policy application

- [ ] Verify domain services functionality

**Notes:** ________________________________________________

### 2.3 File and Storage Services

- [ ] Test file server access from workstations

- [ ] Verify shared drive accessibility

- [ ] Test network drive mapping

- [ ] Verify file server permissions

**Notes:** ________________________________________________

### 2.4 Email Systems

- [ ] Send test email internally

- [ ] Send test email externally

- [ ] Receive test email from external source

- [ ] Test email server connectivity

- [ ] Verify mailbox access

**Notes:** ________________________________________________

### 2.5 Citrix Infrastructure (VLAN 403)

- [ ] Test Citrix server connectivity

- [ ] Verify remote desktop access

- [ ] Test published applications

- [ ] Verify Citrix farm functionality

- [ ] Test user session creation

**Notes:** ________________________________________________

### 2.6 Storage Networks

- [ ] Test iSCSI Network 1 (10.40.110.1) - VLAN 410

- [ ] Test iSCSI Network 2 (10.40.111.1) - VLAN 411

- [ ] Test Nutanix IPMI (10.40.14.1) - VLAN 414

- [ ] Test Nutanix VMotion (10.40.15.1) - VLAN 415

- [ ] Test Nutanix Management (10.40.16.1) - VLAN 416

**Notes:** ________________________________________________

### 2.7 Backup Systems

- [ ] Verify Commvault backup server connectivity

- [ ] Test backup job status

- [ ] Verify backup storage accessibility

- [ ] Test backup server management interface

**Notes:** ________________________________________________

### 2.8 Database Systems

- [ ] Test database server connectivity

- [ ] Verify critical application database access

- [ ] Test database performance

- [ ] Verify database backup connectivity

**Notes:** ________________________________________________

### 2.9 Virtual Infrastructure

- [ ] Test virtual machine creation

- [ ] Verify VMotion functionality

- [ ] Test VM management interface

- [ ] Verify hypervisor connectivity

**Notes:** ________________________________________________

### 2.10 Port Channel Verification

- [ ] Verify HP server port channels (Citrix cluster)

- [ ] Test storage array port channels

- [ ] Verify backup system port channels

- [ ] Test port channel redundancy

**Notes:** ________________________________________________

---

## SECTION 3: VOICE COMMUNICATIONS (HIGH PRIORITY)

### 3.1 Internal VOIP Calling (VLANs 301-322)

- [ ] A Building to AA Building call (VLAN 301 to 302)

- [ ] AA Building to S Building call (VLAN 302 to 303)

- [ ] S Building to H Building call (VLAN 303 to 304)

- [ ] H Building to COS call (VLAN 304 to 305)

- [ ] COS to V Building call (VLAN 305 to 306)

- [ ] V Building to SLC call (VLAN 306 to 307)

- [ ] SLC to B Building call (VLAN 307 to 310)

- [ ] B Building to M Building call (VLAN 310 to 311)

- [ ] M Building to C Building call (VLAN 311 to 312)

- [ ] C Building to E Building call (VLAN 312 to 313)

- [ ] E Building to CAH call (VLAN 313 to 322)

**Notes:** ________________________________________________

### 3.2 External VOIP Calling

- [ ] Outbound call from A Building

- [ ] Outbound call from AA Building

- [ ] Outbound call from S Building

- [ ] Outbound call from H Building

- [ ] Outbound call from administrative buildings

- [ ] Outbound call from academic buildings

**Notes:** ________________________________________________

### 3.3 Advanced VOIP Features

- [ ] Test conference calling capability

- [ ] Verify voicemail system access

- [ ] Test call transfer functionality

- [ ] Verify call forwarding features

- [ ] Test intercom systems

**Notes:** ________________________________________________

---

## SECTION 4: SECURITY SYSTEMS (HIGH PRIORITY)

### 4.1 Security Camera Systems (VLANs 348-353)

- [ ] Test physical security servers (VLAN 348)

- [ ] Verify A and AA building cameras (VLAN 349)

- [ ] Test S, B, H, COS, V, M building cameras (VLAN 350)

- [ ] Verify SLC building cameras (VLAN 351)

- [ ] Test T-building complex cameras (VLAN 352)

- [ ] Verify C, E, Eannex, CAH cameras (VLAN 353)

**Notes:** ________________________________________________

### 4.2 Access Control Systems (VLANs 372-377)

- [ ] Test access control servers (VLAN 372)

- [ ] Verify A and AA building card readers (VLAN 373)

- [ ] Test SLC building access control (VLAN 375)

- [ ] Verify C, E, Eannex, CAH access control (VLAN 377)

- [ ] Test emergency door release systems

**Notes:** ________________________________________________

### 4.3 Security Monitoring

- [ ] Verify security monitoring workstations

- [ ] Test camera feed recording

- [ ] Verify access control logging

- [ ] Test security alert systems

**Notes:** ________________________________________________

---

## SECTION 5: PRINT SERVICES (MEDIUM PRIORITY)

### 5.1 Network Printing (VLAN 402)

- [ ] Test network printer connectivity

- [ ] Verify print queues functionality

- [ ] Test printing from A Building workstations

- [ ] Test printing from AA Building workstations

- [ ] Test printing from administrative workstations

- [ ] Test printing from academic workstations

- [ ] Verify printer management interface

**Notes:** ________________________________________________

---

## SECTION 6: WIRELESS NETWORKS (MEDIUM PRIORITY)

### 6.1 Guest Wireless Networks

- [ ] Test guest WiFi in A Building

- [ ] Test guest WiFi in AA Building

- [ ] Test guest WiFi in academic buildings

- [ ] Test guest WiFi in administrative areas

- [ ] Verify internet access for guests

- [ ] Test guest network isolation

**Notes:** ________________________________________________

### 6.2 Staff Wireless Networks

- [ ] Test staff WiFi authentication

- [ ] Verify staff network access in A Building

- [ ] Test staff network access in AA Building

- [ ] Test staff network access in academic areas

- [ ] Verify staff network resource access

**Notes:** ________________________________________________

### 6.3 Student Wireless Networks (VLANs 200-204)

- [ ] Test SLC student network (VLAN 200)

- [ ] Test SLC Aruba student network (VLAN 201)

- [ ] Test SLC staff Aruba network (VLAN 202)

- [ ] Test SLC appliance network (VLAN 203)

- [ ] Test SLC guest Aruba network (VLAN 204)

**Notes:** ________________________________________________

---

## SECTION 7: NETWORK SERVICES (MEDIUM PRIORITY)

### 7.1 Inter-Building Connectivity

- [ ] Test connectivity from A Building to other buildings

- [ ] Test connectivity from AA Building to other buildings

- [ ] Test connectivity between academic buildings

- [ ] Test connectivity between administrative buildings

- [ ] Verify routing between all building networks

**Notes:** ________________________________________________

### 7.2 DHCP Services

- [ ] Test DHCP functionality in VLAN 301 (A Building VOIP)

- [ ] Test DHCP functionality in VLAN 302 (AA Building VOIP)

- [ ] Test DHCP functionality in server VLANs

- [ ] Test DHCP functionality in wireless VLANs

- [ ] Verify DHCP helper addresses working

**Notes:** ________________________________________________

### 7.3 DNS Services

- [ ] Test internal DNS resolution

- [ ] Test external DNS resolution (google.com)

- [ ] Verify DNS server connectivity

- [ ] Test reverse DNS lookups

**Notes:** ________________________________________________

### 7.4 Internet Connectivity

- [ ] Test internet from A Building

- [ ] Test internet from AA Building

- [ ] Test internet from server VLANs

- [ ] Test internet from wireless networks

- [ ] Verify internet routing path

**Notes:** ________________________________________________

### 7.5 Network Management

- [ ] Access switch management interfaces

- [ ] Test network monitoring tools

- [ ] Verify SNMP functionality

- [ ] Test network performance monitoring

**Notes:** ________________________________________________

---

## SECTION 8: VLAN CONNECTIVITY TESTING (MEDIUM PRIORITY)

### 8.1 Management and Core VLANs

- [ ] VLAN 1 (Default) - Test connectivity to 192.168.2.210 (management)

- [ ] VLAN 2 (SAN00) - Test connectivity to 172.16.13.1 (storage network)

- [ ] VLAN 120 (E102-Cytek-Crap) - Test connectivity to 10.1.20.1 (lab network)

**Test Commands:**

```

ping 192.168.2.210

ping 172.16.13.1

ping 10.1.20.1

```

**Notes:** ________________________________________________

### 8.2 WAN and Internet VLANs

- [ ] VLAN 10 (VideoVLAN10) - Secondary WAN connectivity test

- [ ] VLAN 50 (DMZ) - DMZ network connectivity test

- [ ] VLAN 51 (DMZ2) - Secondary DMZ connectivity test

- [ ] VLAN 100 (SWKO) - Primary WAN connectivity test

- [ ] VLAN 150 (ASA-LAN-FO) - Firewall failover connectivity

- [ ] VLAN 151 (ASA-STFUL-FO) - Firewall stateful failover connectivity

**Test Commands:**

```

# Test from internal networks to verify WAN/DMZ routing

tracert 8.8.8.8 (should show WAN path)

```

**Notes:** ________________________________________________

### 8.3 Student Network VLANs (200-204)

- [ ] VLAN 200 (SLC_students) - Student network connectivity

- [ ] VLAN 201 (SLC-Students-Aruba) - Aruba student network connectivity

- [ ] VLAN 202 (SLC-Staff-Aruba) - Aruba staff network connectivity

- [ ] VLAN 203 (SLC-Appliance-Aruba) - Aruba appliance network connectivity

- [ ] VLAN 204 (SLC-Guest-Aruba) - Aruba guest network connectivity

**Test Commands:**

```

# Test DHCP and internet access from student devices

ipconfig /all (verify DHCP assignment)

ping 8.8.8.8 (verify internet access)

```

**Notes:** ________________________________________________

### 8.4 VOIP Network VLANs (301-322, 332)

- [ ] VLAN 301 (VOIP-A) - Test connectivity to 10.30.1.1 (A Building)

- [ ] VLAN 302 (VOIP-AA) - Test connectivity to 10.30.2.1 (AA Building)

- [ ] VLAN 303 (VOIP-S) - Test connectivity to 10.30.3.1 (S Building)

- [ ] VLAN 304 (VOIP-H) - Test connectivity to 10.30.4.1 (H Building)

- [ ] VLAN 305 (VOIP-COS) - Test connectivity to 10.30.5.1 (COS109)

- [ ] VLAN 306 (VOIP-V) - Test connectivity to 10.30.6.1 (V201 & GH2)

- [ ] VLAN 307 (VOIP-SLC) - Test connectivity to 10.30.7.1 (SLC151)

- [ ] VLAN 308 (VOIP-SLCCDE) - Test connectivity to 10.30.8.1 (SLCCDE)

- [ ] VLAN 309 (VOIP-SLCAB) - Test connectivity to 10.30.9.1 (SLCAB)

- [ ] VLAN 310 (VOIP-B) - Test connectivity to 10.30.10.1 (B101)

- [ ] VLAN 311 (VOIP-M) - Test connectivity to 10.30.11.1 (M201)

- [ ] VLAN 312 (VOIP-C) - Test connectivity to 10.30.12.1 (C105)

- [ ] VLAN 313 (VOIP-E) - Test connectivity to 10.30.13.1 (E208)

- [ ] VLAN 314 (VOIP-EA) - Test connectivity to 10.30.14.1 (Eannex)

- [ ] VLAN 322 (VOIP-CAH) - Test connectivity to 10.30.22.1 (CAH144)

- [ ] VLAN 332 (TestingAndGI) - Test connectivity to 10.30.32.1 (Testing/GI)

**Test Commands:**

```

ping 10.30.1.1    # A Building VOIP

ping 10.30.2.1    # AA Building VOIP

ping 10.30.3.1    # S Building VOIP

ping 10.30.4.1    # H Building VOIP

ping 10.30.5.1    # COS Building VOIP

ping 10.30.6.1    # V Building VOIP

ping 10.30.7.1    # SLC Building VOIP

ping 10.30.8.1    # SLCCDE VOIP

ping 10.30.9.1    # SLCAB VOIP

ping 10.30.10.1   # B Building VOIP

ping 10.30.11.1   # M Building VOIP

ping 10.30.12.1   # C Building VOIP

ping 10.30.13.1   # E Building VOIP

ping 10.30.14.1   # Eannex VOIP

ping 10.30.22.1   # CAH Building VOIP

ping 10.30.32.1   # Testing/GI VOIP

```

**Notes:** ________________________________________________

### 8.5 Security Camera VLANs (348-353)

- [ ] VLAN 348 (PSEC-Servers) - Test connectivity to 10.30.48.1 (Physical Security Servers)

- [ ] VLAN 349 (PSEC-A-AA) - Test connectivity to 10.30.49.1 (A, AA Buildings cameras)

- [ ] VLAN 350 (PSEC-S-B-H-Cos-V-M) - Test connectivity to 10.30.50.1 (Multiple buildings)

- [ ] VLAN 351 (PSEC-SLC) - Test connectivity to 10.30.51.1 (SLC Buildings cameras)

- [ ] VLAN 352 (PSEC-T-TA-TB-TD-TT) - Test connectivity to 10.30.52.1 (T Buildings)

- [ ] VLAN 353 (PSEC-C-E-EAnnex-CAH) - Test connectivity to 10.30.53.1 (Academic buildings)

**Test Commands:**

```

ping 10.30.48.1   # Security servers

ping 10.30.49.1   # A, AA cameras

ping 10.30.50.1   # S, B, H, COS, V, M cameras

ping 10.30.51.1   # SLC cameras

ping 10.30.52.1   # T-building cameras

ping 10.30.53.1   # C, E, Eannex, CAH cameras

```

**Notes:** ________________________________________________

### 8.6 Access Control VLANs (372-377)

- [ ] VLAN 372 (DAC-Servers) - Test connectivity to 10.30.72.1 (Access Control Servers)

- [ ] VLAN 373 (DAC-A-AA) - Test connectivity to 10.30.73.1 (A, AA Buildings access)

- [ ] VLAN 375 (SC-IoT/DAC-SLC) - Test connectivity to 10.30.75.1 (SLC access control)

- [ ] VLAN 377 (DAC-C-E-Eannex-CAH) - Test connectivity to 10.30.77.1 (Academic access control)

**Test Commands:**

```

ping 10.30.72.1   # Access control servers

ping 10.30.73.1   # A, AA access control

ping 10.30.75.1   # SLC access control

ping 10.30.77.1   # C, E, Eannex, CAH access control

```

**Notes:** ________________________________________________

### 8.7 Server Infrastructure VLANs (401-416)

- [ ] VLAN 401 (Servers) - Test connectivity to 10.40.1.1 (Main Server VLAN)

- [ ] VLAN 402 (Printers) - Test connectivity to 10.40.2.1 (Printer VLAN)

- [ ] VLAN 403 (Citrix) - Test connectivity to 10.40.3.1 (HP Equipment/Citrix)

- [ ] VLAN 404 (VMotionLive) - Test connectivity to 10.40.4.1 (VMotion Live)

- [ ] VLAN 405 (DigitalSignage) - Test connectivity to 10.40.5.1 (Digital Signage)

- [ ] VLAN 410 (HPiSCSI-410) - Test connectivity to 10.40.110.1 (iSCSI Network 1)

- [ ] VLAN 411 (HPiSCSI-411) - Test connectivity to 10.40.111.1 (iSCSI Network 2)

- [ ] VLAN 414 (Nutan-IPMI) - Test connectivity to 10.40.14.1 (Nutanix IPMI)

- [ ] VLAN 415 (Nutan-VMWareVmotion) - Test connectivity to 10.40.15.1 (Nutanix VMotion)

- [ ] VLAN 416 (Nutan-VMMgmtCVMClst) - Test connectivity to 10.40.16.1 (Nutanix Management)

**Test Commands:**

```

ping 10.40.1.1    # Main servers

ping 10.40.2.1    # Printers

ping 10.40.3.1    # Citrix servers

ping 10.40.4.1    # VMotion network

ping 10.40.5.1    # Digital signage

ping 10.40.110.1  # iSCSI Network 1

ping 10.40.111.1  # iSCSI Network 2

ping 10.40.14.1   # Nutanix IPMI

ping 10.40.15.1   # Nutanix VMotion

ping 10.40.16.1   # Nutanix Management

```

**Notes:** ________________________________________________

### 8.8 Wireless Network VLANs (500-522)

- [ ] VLAN 501 (Wireless2) - Test connectivity to 10.50.1.1 (Wireless Network 2)

- [ ] VLAN 502 (WLAN-APs-WCS) - Test connectivity to 10.50.2.1 (AP Management)

- [ ] VLAN 504 (WLAN-Private) - Test connectivity to 10.50.4.1 (Private Wireless)

- [ ] VLAN 506 (WLAN-IPads) - Test connectivity to 10.50.6.1 (iPad Network)

- [ ] VLAN 508 (WLAN-Public) - Test connectivity to 10.50.8.1 (Public Wireless)

**Test Commands:**

```

ping 10.50.1.1    # Wireless network 2

ping 10.50.2.1    # AP management

ping 10.50.4.1    # Private wireless

ping 10.50.6.1    # iPad network

ping 10.50.8.1    # Public wireless

```

**Notes:** ________________________________________________

### 8.9 Building Network VLANs (600-845)

- [ ] VLAN 601 (firewalls) - Firewall connectivity

- [ ] VLAN 610 (IT-Staff) - IT Staff network connectivity

- [ ] VLAN 701 (A-building) - A Building network connectivity

- [ ] VLAN 702 (AA-building) - AA Building network connectivity

- [ ] VLAN 703 (S-building) - S Building network connectivity

- [ ] VLAN 722 (Aruba-APs-H) - H Building Aruba APs

- [ ] VLAN 750 (Aruba-APs-V-COS) - V and COS Building APs

- [ ] VLAN 766 (Aruba-APs-SLC151) - SLC151 Aruba APs

- [ ] VLAN 775 (Aruba-APs-SLCCDE) - SLCCDE Aruba APs

- [ ] VLAN 791 (Aruba-APs-SLCAB) - SLCAB Aruba APs

- [ ] VLAN 806 (Aruba-APs-B) - B Building Aruba APs

- [ ] VLAN 817 (HVAC) - HVAC control systems

- [ ] VLAN 818 (Fire-Alarms) - Fire alarm systems

- [ ] VLAN 819 (Boilers) - Boiler control systems

- [ ] VLAN 824 (SLC-152-building) - SLC 152 Building

- [ ] VLAN 826 (Aruba-APs-M) - M Building Aruba APs

- [ ] VLAN 835 (Aruba-APs-C) - C Building Aruba APs

- [ ] VLAN 845 (Aruba-APs-E-EAnnex-CAH) - E, EAnnex, CAH Aruba APs

**Test Commands:**

```

# Test building networks (specific IPs may vary)

ping [building_gateway_ip]

# Test AP management networks

ping [ap_management_ip]

# Test HVAC and fire systems

ping [hvac_controller_ip]

ping [fire_alarm_panel_ip]

```

**Notes:** ________________________________________________

### 8.10 VLAN Routing and Inter-VLAN Communication

- [ ] Test routing between VOIP VLANs (301-322)

- [ ] Test routing between server VLANs (401-416)

- [ ] Test routing between building VLANs (701-845)

- [ ] Test routing from user VLANs to server VLANs

- [ ] Test routing from wireless VLANs to internet

- [ ] Verify VLAN isolation where required (guest networks)

- [ ] Test multicast routing for VOIP VLANs

**Test Commands:**

```

# Inter-VLAN routing tests

ping [target_vlan_gateway] from [source_vlan]

tracert [target_vlan_ip] from [source_vlan]

# Multicast tests for VOIP

# Test SIP registration and call setup

```

**Notes:** ________________________________________________

### 8.11 DHCP Helper and Service Verification per VLAN

- [ ] Verify DHCP helper addresses working for VOIP VLANs (10.40.1.40, 10.40.1.70, 192.168.1.112)

- [ ] Test DHCP assignment in building VLANs

- [ ] Verify DHCP scope availability for each VLAN

- [ ] Test DHCP failover between helper addresses

- [ ] Verify DNS assignment via DHCP

**Test Commands:**

```

ipconfig /release

ipconfig /renew

ipconfig /all (verify DHCP server and DNS servers)

nslookup [hostname] (verify DNS from DHCP)

```

**Notes:** ________________________________________________

---

## SECTION 9: BUILDING-SPECIFIC TESTING (LOW PRIORITY)

### 9.1 A Building Complete Systems Test

- [ ] VOIP system (VLAN 301)

- [ ] Security cameras (VLAN 349)

- [ ] Access control systems

- [ ] Wireless connectivity

- [ ] Workstation network access

**Notes:** ________________________________________________

### 9.2 AA Building Complete Systems Test

- [ ] VOIP system (VLAN 302)

- [ ] Security cameras (VLAN 349)

- [ ] Access control systems

- [ ] Wireless connectivity

- [ ] Workstation network access

**Notes:** ________________________________________________

### 9.3 SLC Buildings Complete Systems Test

- [ ] VOIP systems (VLANs 307-309, 321)

- [ ] Security cameras (VLAN 351)

- [ ] Student networks (VLANs 200-204)

- [ ] Wireless connectivity

- [ ] Academic workstation access

**Notes:** ________________________________________________

### 9.4 T-Building Complex Complete Systems Test

- [ ] VOIP systems (VLANs 316-320)

- [ ] Security cameras (VLAN 352)

- [ ] Access control systems

- [ ] Wireless connectivity

**Notes:** ________________________________________________

### 9.5 CAH Building Complete Systems Test

- [ ] VOIP system (VLAN 322)

- [ ] Security cameras (VLAN 353)

- [ ] Access control systems

- [ ] Wireless connectivity

**Notes:** ________________________________________________

---

## SECTION 10: ADDITIONAL SERVICES (LOW PRIORITY)

### 10.1 Digital Signage (VLAN 405)

- [ ] Test digital signage in A Building

- [ ] Test digital signage in AA Building

- [ ] Test digital signage in academic buildings

- [ ] Test digital signage in common areas

**Notes:** ________________________________________________

### 10.2 Time Synchronization

- [ ] Verify NTP server connectivity

- [ ] Test time synchronization on switches

- [ ] Verify time synchronization on servers

- [ ] Test time synchronization on workstations

**Notes:** ________________________________________________

### 10.3 Performance Monitoring

- [ ] Monitor network latency

- [ ] Check for packet loss

- [ ] Verify network utilization levels

- [ ] Test network performance under load

**Notes:** ________________________________________________

### 10.4 Security Monitoring

- [ ] Verify security monitoring systems operational

- [ ] Test security alert mechanisms

- [ ] Verify log collection systems

- [ ] Test incident response procedures

**Notes:** ________________________________________________

---

## SECTION 11: FINAL VERIFICATION

### 11.1 Routing and Connectivity

- [ ] Review routing tables

- [ ] Verify all network segments reachable

- [ ] Test redundant path functionality

- [ ] Verify load balancing if configured

**Notes:** ________________________________________________

### 11.2 Documentation and Reporting

- [ ] Document all test results

- [ ] Record any issues found

- [ ] Create follow-up action items

- [ ] Update network documentation

**Notes:** ________________________________________________

---

## TESTING SUMMARY

**Total Tests Completed:** _____ / _____

**Tests Passed:** _____

**Tests Failed:** _____

**Tests Requiring Follow-up:** _____

### Critical Issues Found:

1. ________________________________________________

2. ________________________________________________

3. ________________________________________________

### High Priority Issues Found:

1. ________________________________________________

2. ________________________________________________

3. ________________________________________________

### Follow-up Actions Required:

1. ________________________________________________

2. ________________________________________________

3. ________________________________________________

**Testing Completed by:** _______________

**Date:** _______________

**Signature:** _______________

APPENDIX – B

VSF-Aware Phase Configuration Summary

## High Availability Network Migration Strategy for SCCC

### Overview

This document summarizes the complete VSF-aware phase configuration strategy for migrating from a failing Cisco 4510 core switch to a high-availability dual Aruba 6300 VSF infrastructure. The approach combines **incremental service migration** with **VSF high availability** to provide maximum safety and reliability.

---

## Configuration File Structure

### Foundation Files

1. **`SW-AA144-VSF-Configuration.cfg`** - VSF stack formation (prerequisite)

2. **`SW-AA144-VSF-Main-Config.cfg`** - Complete production configuration (reference)

### Phase-Specific VSF Configurations

3. **`Phase1_VSF_Foundation_Config.cfg`** - Foundation infrastructure

4. **`Phase2_VSF_NonCritical_Config.cfg`** - Non-critical services

5. **`Phase3_VSF_Security_Wireless_Config.cfg`** - Security and wireless

6. **`Phase4_VSF_VoIP_Config.cfg`** - VoIP and phone systems

7. **`VSF_Phase_Configuration_Summary.md`** - This summary document

---

## Phase-by-Phase Configuration Strategy

### Phase 1: Foundation Infrastructure ⚡

**Duration:** 2-3 hours | **Impact:** Minimal | **Rollback:** Full

#### What's Configured:

- ✅ **Management VLANs:** 1, 2, 17, 51, 150, 151

- ✅ **Basic Routing:** OSPF 100, default route

- ✅ **VSF Management:** Cross-member management connections

- ✅ **Essential Services:** NTP, DNS, SSH, HTTPS

- ✅ **Security:** Management access control

- ✅ **Monitoring:** Logging, SNMP

#### VSF-Specific Features:

- **Dual management connections** (1/1/46 & 2/1/46)

- **Cross-member console access** (1/1/45 & 2/1/45)

- **VSF-aware spanning tree** priorities

- **Unified management** with automatic sync

#### Success Criteria:

- VSF stack healthy and both members active

- Management IP reachable from both members

- NTP/DNS working properly

- All foundation services operational

---

### Phase 2: Non-Critical Services 🟢

**Duration:** 3-4 hours | **Impact:** Minimal | **Rollback:** By service

#### What's Configured:

- ✅ **Student Networks:** VLANs 200-204 with filtering

- ✅ **Lab Networks:** VLANs 800-805 with restrictions

- ✅ **Guest Networks:** VLANs 603-605 with isolation

- ✅ **Wireless Management:** VLANs 601-605

- ✅ **Media Networks:** VLANs 10, 999

- ✅ **General Purpose:** VLANs 100, 332

#### VSF-Specific Features:

- **Distributed access ports** across both VSF members

- **Cross-member guest access** (1/1/43 & 2/1/43)

- **Balanced student connections** (1/1/44 & 2/1/44)

- **Separate OSPF process** for lab networks (OSPF 200)

- **Independent QoS policies** for different user types

#### Security Features:

- **Guest internet-only access** with RFC1918 blocking

- **Lab network restrictions** with controlled access

- **Student network filtering** with limited admin access

- **Bandwidth limiting** for guest and lab traffic

---

### Phase 3: Security and Wireless 🔐

**Duration:** 3-4 hours | **Impact:** Low-Medium | **Rollback:** By system

#### What's Configured:

- ✅ **Security Cameras:** VLANs 348-353 with LAG redundancy

- ✅ **Building Networks:** VLANs 501-522 for all buildings

- ✅ **CAH Building:** VLANs 120, 840-845

- ✅ **Access Control:** Door systems, alarms, panic buttons

- ✅ **Wireless Infrastructure:** Distributed AP connections

#### VSF-Specific Features:

- **Redundant security LAGs** (100-103) across VSF members

- **Distributed building APs** (1/1/31-33 & 2/1/31-33)

- **Cross-member security systems** for high availability

- **Separate OSPF process** for wireless (OSPF 300)

#### High Availability Security:

- **Dual security camera LAGs** (Primary: LAG 100, Secondary: LAG 101)

- **Redundant door access** (Primary: LAG 102, Secondary: LAG 103)

- **Panic system priority** QoS with highest priority

- **Building-specific wireless** with failover protection

---

### Phase 4: VoIP and Phone Systems 📞

**Duration:** 4-5 hours | **Impact:** High | **Rollback:** By building

#### What's Configured:

- ✅ **VoIP Networks:** All VLANs 301-322 (22 VoIP networks)

- ✅ **Phone Systems:** All campus buildings

- ✅ **VoIP Gateways:** Redundant LAGs 200-201

- ✅ **Multicast:** PIM routing for VoIP services

- ✅ **QoS:** Voice traffic prioritization

#### VSF-Specific Features:

- **Dual VoIP gateway LAGs** across VSF members

- **Building-specific VoIP** connections (1/1/11-16 & 2/1/11-16)

- **Cross-member voice redundancy** for all buildings

- **Optimized spanning tree** for voice (priority 0)

- **Voice-specific security** policies

#### Critical VoIP Features:

- **Highest priority QoS** for voice traffic (EF/CS5)

- **Multicast routing** for voice services

- **Voice VLAN optimization** with fast convergence

- **Building-by-building rollback** capability

- **Emergency phone protection** with panic system integration

---

## VSF Architecture Benefits

### High Availability Advantages

| Feature | Non-VSF | VSF-Aware |

|---------|---------|-----------|

| **Switch Failure** | Complete outage | Automatic failover |

| **Management** | Two IP addresses | Single IP address |

| **Configuration** | Separate configs | Unified configuration |

| **Port Density** | 48 ports each | 94 ports combined |

| **Failover Time** | Manual intervention | Sub-second automatic |

| **Monitoring** | Separate systems | Unified monitoring |

### VSF-Specific Design Elements

#### Port Distribution Strategy:

- **VSF Links:** Ports 48, 49, 50 (triple redundancy)

- **Management:** Ports 45, 46 (dual connections)

- **Critical Services:** Distributed across both members

- **Server Infrastructure:** Cross-member LAGs

- **User Access:** Balanced across both switches

#### Network Resilience:

- **VoIP Gateway:** Dual LAGs (200-201) across members

- **Security Systems:** Redundant LAGs (100-103)

- **Building Networks:** Dual connections per building

- **Wireless Infrastructure:** Cross-member AP connections

- **Internet/Firewall:** Redundant uplinks (1/1/47 & 2/1/47)

---

## Implementation Timeline

### Pre-Migration Phase (1-2 weeks)

- [ ] **Install VSF cables** between switches

- [ ] **Verify firmware compatibility** on both switches

- [ ] **Plan cable management** for VSF links

- [ ] **Schedule maintenance windows** for each phase

- [ ] **Prepare rollback procedures** for each phase

### Migration Execution (6-8 weeks)

- **Week 1:** VSF Formation + Phase 1 (Foundation)

- **Week 2:** Phase 2 (Non-Critical Services)

- **Week 3:** Phase 3 (Security & Wireless)

- **Week 4:** Phase 4 (VoIP Systems) - CRITICAL

- **Week 5:** Phase 5 (Server Infrastructure) - CRITICAL

- **Week 6:** Phase 6 (Final Cutover) - CRITICAL

### Post-Migration Phase (2 weeks)

- [ ] **Monitor VSF health** and performance

- [ ] **Fine-tune QoS policies** based on traffic patterns

- [ ] **Optimize spanning tree** for better convergence

- [ ] **Document final configuration** and procedures

- [ ] **Train operations team** on VSF management

---

## Risk Mitigation Strategy

### Eliminated Risks with VSF:

- ✅ **Single Switch Failure:** Automatic failover eliminates downtime

- ✅ **Management Complexity:** Single IP for both switches

- ✅ **Configuration Drift:** Automatic synchronization

- ✅ **Port Limitations:** Combined port capacity

- ✅ **Manual Failover:** Sub-second automatic switching

### Enhanced Safety Features:

- **Gradual Rollback:** Each phase can be rolled back independently

- **Service Isolation:** Problems in one phase don't affect others

- **Cross-Member Redundancy:** Critical services span both switches

- **Real-Time Monitoring:** VSF health monitoring at each phase

- **Incremental Testing:** Each phase tested before proceeding

---

## Verification Strategy

### Per-Phase Verification:

1. **VSF Health Check:** `show vsf`, `show vsf member`, `show vsf topology`

2. **Service Connectivity:** Test all new services added in phase

3. **Failover Testing:** Simulate member failure and recovery

4. **Performance Validation:** Monitor latency, throughput, packet loss

5. **Security Verification:** Test access controls and filtering

### Continuous Monitoring:

- **VSF Link Utilization:** Monitor 30 Gbps link capacity

- **Member Load Balancing:** Ensure even distribution

- **Failover Events:** Log and analyze any automatic failovers

- **Configuration Sync:** Verify automatic synchronization

- **Performance Metrics:** Track network performance improvements

---

## Expected Outcomes

### Network Reliability Improvements:

- **Availability:** 99.9%+ uptime (up from 95% with single switch)

- **Failover Time:** <1 second (vs. hours of manual intervention)

- **Capacity:** 94 ports (vs. 48 ports single switch)

- **Throughput:** Combined switching capacity of both switches

- **Scalability:** Room for future expansion without major changes

### Operational Benefits:

- **Simplified Management:** Single configuration file

- **Reduced Complexity:** Unified monitoring and troubleshooting

- **Faster Recovery:** Automatic failover and recovery

- **Enhanced Security:** Centralized policy management

- **Future-Proof:** ISSU support for seamless upgrades

---

## Success Metrics

### Technical Metrics:

- **VSF Uptime:** 99.9% VSF stack availability

- **Failover Performance:** <1 second convergence time

- **Network Utilization:** Balanced traffic across both members

- **Service Quality:** Voice quality maintained during failover

- **Security Posture:** No security incidents during migration

### Business Metrics:

- **Phone Service:** 100% phone functionality maintained

- **Internet Access:** No internet service interruptions

- **Security Systems:** All cameras and access control operational

- **User Productivity:** Minimal impact on daily operations

- **Cost Efficiency:** No additional hardware purchases needed

---

## Conclusion

This VSF-aware phase configuration strategy provides:

1. **Maximum Safety:** Incremental migration with full rollback capability

2. **High Availability:** Automatic failover eliminates single points of failure

3. **Operational Simplicity:** Single management interface for dual-switch infrastructure

4. **Service Continuity:** Minimal disruption to critical campus services

5. **Future Readiness:** Scalable architecture supporting campus growth

The combination of **VSF high availability** with **phased migration** transforms what could be a risky "big bang" cutover into a **safe, manageable process** that ensures continuous operation of critical campus infrastructure.

**Ready for Implementation:** All configuration files are production-ready and include comprehensive verification procedures and rollback plans.